V5 — REMA Stakeholder Flowchart

Node Label Explanations

# 🔴  LANE 1 — Red Cross Operations Center

## Phase 0 — Dry Season Preparedness

| Subscribe Alerts | Red Cross subscribes to VNHMDS automated flood alerts and activates the 2-of-3 trigger watch at the start of flood season (May–November). |
| --- | --- |
| Sign MOUs | Partnerships Officer signs 8 pre-flood agreements: sub-warehouse site access, household data sharing, boat owners, truck contractors, pharmacy distributors, MoH, radio frequencies, and volunteer registration. |
| Confirm WH Stock | Warehouse Manager verifies central warehouse stock is at minimum threshold and all EMK-1, EMK-2, and EMK-3 kits are assembled and labeled. |
| ⚡ TRIGGER WATCH | Emergency Coordinator monitors VNHMDS alerts daily. REMA activates when any 2 of 3 conditions are met simultaneously: flood warning Level 2+, rainfall forecast >100mm/24h, or street flooding reported. |
| Dry-Season Renewal | Annual renewal checklist: all MOUs reviewed and re-signed, stock replenished, forms reprinted, radio equipment tested, vulnerability maps updated. |

## Phase 1 — Hours 0–24: Activate & Pre-Position

| ⚡ ACTIVATION TRIGGER | The 2-of-3 trigger is met. Emergency Coordinator issues the REMA Activation Order within Hours 0–3. All sub-warehouse managers notified by SMS. |
| --- | --- |
| Continue Monitoring | Fewer than 2 conditions met — no activation. Trigger watch continues. |
| Issue Activation Order | Emergency Coordinator formally activates REMA. Triggers simultaneous actions: SMS to Hub Managers, EMK-3 request to MoH, truck dispatch order. |
| Request MoH EMK-3 | Operations Center contacts Ministry of Health to release EMK-3 medication stock from district cold storage. Transfer must reach sub-warehouses within 6 hours of activation. |
| Approve Truck Dispatch | Emergency Coordinator approves convoy of 3 trucks to depart central warehouse simultaneously, one per district sub-warehouse. Highest-elevation routes. Hours 3–8. |

## Phase 2 — Hours 24–48+: Deliver & Adapt

| Receive Demand Summary | Hub Managers send SMS/WhatsApp demand summaries to Operations Center at Hours 16–24, based on compiled volunteer assessment forms. |
| --- | --- |
| Stock below 30%? | Operations Center checks whether total stock across any sub-warehouse has fallen below 30% of the original dispatch allocation. |
| ⚠ SCARCITY MODE | If stock falls below 30%: EMK-1 community collection points suspended, all remaining stock redirected to Medium band and above, MoH notified for emergency resupply. |
| Approve Reallocation | Emergency Coordinator approves cross-district stock reallocation within 2 hours of request from any Hub Manager. Stock moved from central 30% reserve. |
| Water >80cm? | Operations Center checks whether any zone has water depth exceeding 80cm — the hard safety limit for volunteer delivery. |
| Escalate to Civil Defense | If water exceeds 80cm in any zone: delivery suspended, civil defense notified for evacuation support, affected households contacted by phone if network available. |
| Situation Report | Operations Center issues a consolidated situation report every 6 hours, shared with all actor groups: Hub Managers, MoH, ward health stations, civil defense. |

# 🟠  LANE 2 — Hub Managers

## Phase 0 — Dry Season Preparedness

| Inspect Sub-WH Sites | Hub Managers physically inspect each sub-warehouse building (ward office, school, community hall) to confirm it is elevated, accessible by truck, and has 40–60 sqm of dry floor space. |
| --- | --- |
| Update Vulnerability Maps | Hub Managers update ward-level vulnerability maps annually with ward health workers — identifying households with elderly, pregnant women, infants, disabled persons, and chronic illness. |
| Pre-print Forms | All paper forms printed before flood season: household assessment forms, delivery receipts, stock ledgers, incident logs, radio scripts. 20% excess copies stored at each sub-warehouse. |
| Confirm Volunteer Roster | Hub Manager confirms active volunteer roster of 45 names (12 per sub-warehouse + 20% buffer). Volunteers trained twice per year. |
| Sub-WH Setup Checklist | Sub-warehouse setup checklist template ready, stock ledger pre-formatted, radio equipment tested and frequency confirmed. |

## Phase 1 — Hours 0–24

| Standby Alert | Hub Manager receives SMS activation from Operations Center at Hours 0–3. Puts volunteer team leaders on standby. |
| --- | --- |
| Receive EMK Pallets | Hub Manager receives EMK pallet delivery from truck convoy at Hours 3–8. Verifies count against printed dispatch manifest. 5% spot-check of boxes. Signs receipt. |
| Setup Sub-Warehouse | Sub-warehouse configured: EMK-1, EMK-2, EMK-3 separated into labeled zones, volunteer check-in table set up at entrance, district map posted on wall, radio contact with Operations Center confirmed. |
| Deploy Volunteer Teams | Volunteer teams deployed for community assessment (not delivery yet) at Hours 8–16. Teams assigned to CROSS-WARD zones — volunteers assess wards they are not from, reducing favoritism. |
| Compile Assessment Forms | Hub Manager collects paper assessment forms from volunteers every 4 hours. Compiles district-level demand estimates. Sends SMS/WhatsApp summary to Operations Center at Hours 16–24. |

## Phase 2 — Hours 24–48+

| Assign Delivery Runs | Hub Manager assigns delivery runs at fixed departure times: 7am, 11am, 3pm. Each team receives a prioritized household list for their zone. |
| --- | --- |
| Radio Check-ins | Hub Manager reports to Operations Center by radio at 08:00, 12:00, 16:00, and 20:00 daily. Fixed-format script covers stock levels, incidents, route issues, and next-run plan. |
| Zone Inaccessible? | Hub Manager checks whether an entire delivery zone is unreachable by any surface route. |
| Adaptive Routing | Hub Manager redirects stock between delivery teams, opens unplanned community collection points, and adjusts routes in real time based on volunteer reports. No approval needed. |
| Request Boat | If a zone is entirely inaccessible by surface: Hub Manager requests boat deployment from Operations Center or an adjacent sub-warehouse. |
| Sub-WH Flooded? | If boat request cannot resolve zone access: Hub Manager checks whether the sub-warehouse building itself is flooded or inaccessible. |
| Activate Backup Sub-WH | If sub-warehouse is flooded: Hub Manager activates the pre-identified backup site (arranged in Phase 0). All volunteers notified of new pickup point by SMS or radio. Operations Center updates dashboard. |

# 🟣  LANE 3 — Volunteers

## Phase 0 — Dry Season Preparedness

| Training | Volunteers attend two training sessions per year. Covers household assessment form completion, scoring criteria, delivery protocol, and volunteer safety rules. |
| --- | --- |
| Vulnerability Mapping | Volunteers assist ward health workers to update vulnerability maps in their ASSIGNED wards — identifying elderly, pregnant women, infants, disabled persons, and known chronic illness cases. |
| Confirm Availability | Volunteers confirm availability for the upcoming flood season, update contact information, and re-sign volunteer registration forms. |

## Phase 1 — Hours 0–24

| Deployment Briefing | Volunteers receive 15-minute briefing from Hub Manager at Hour 8. Covers zone assignment, assessment form instructions, safety rules, and radio check-in times. |
| --- | --- |
| ★ CROSS-WARD Assignment | Volunteers are assigned to wards they do not live in. This is a deliberate fairness safeguard — it reduces favoritism and personal bias in household prioritization. |
| Assess Households | Volunteers complete 10-question paper assessment form at each household. Takes approximately 3 minutes. Covers medical urgency, vulnerability, flood exposure, self-sufficiency, and isolation. Hours 8–16. |
| Return Forms | Volunteers return completed assessment forms to Hub Manager every 4 hours. Also report new critical cases verbally that were not on the pre-mapped list. |

## Phase 2 — Hours 24–48+

| Collect Priority List | Volunteer team collects the prioritized household delivery list and correct EMK stock from the sub-warehouse before each run. |
| --- | --- |
| Water Depth? | Team leader assesses current water depth in the delivery zone to determine which transport mode is safe. |
| 0–30cm: Motorbike | Water depth 0–30cm: volunteer delivers by motorbike with waterproof pannier bags. Fastest mode. |
| 30–60cm: Bicycle / Foot | Water depth 30–60cm: volunteer delivers by cargo bicycle or on foot with waterproof backpack. |
| 60–80cm: Boat | Water depth 60–80cm: volunteer delivers by small motorized boat or inflatable raft arranged with community boat owners. |
| >80cm: ⚠ SUSPEND | Water depth above 80cm: all delivery suspended immediately. Volunteer team returns to sub-warehouse or shelters in place. Hub Manager notified. Civil defense escalation triggered. |
| Deliver EMK | Volunteer confirms household identity (name and address on priority list), delivers the correct EMK type (EMK-1, 2, or 3), and collects a signed or thumbprinted receipt. |
| Report New Cases | On returning to sub-warehouse, volunteer verbally reports new critical cases discovered during the run that were not on the priority list. Hub Manager logs these for the next delivery run. |

# 🔵  LANE 4 — Health Facilities

## Phase 0 — Dry Season Preparedness

| Vulnerability Mapping Support | Ward health workers assist volunteers to update vulnerability maps — confirming which households have chronic illness cases and what medications are required. |
| --- | --- |
| Confirm Medication List | Ward health station confirms which chronic illness medications are most urgently needed in each ward. This list feeds into EMK-3 pre-positioning and MoH request. |
| Referral Card Info | Health facilities provide up-to-date contact information (phone, location) for EMK-3 referral cards included in every chronic illness kit. Updated annually. |
| Confirm Station Staffing | Each ward health station confirms that at least one health station per district will remain staffed above flood level throughout the 5–7 day flood event. |

## Phase 1 — Hours 0–24

| Receive Referrals | Ward health stations receive clinical referrals from volunteers for cases that are beyond the scope of EMK contents — requiring diagnosis, prescription, or clinical assessment. From Hour 8 onward. |
| --- | --- |
| Liaise with MoH | Health facilities liaise with Ministry of Health to confirm the EMK-3 medication list and validate drug priorities before activation. Ensures MoH cold storage holds the right medications. |

## Phase 2 — Hours 24–48+

| Clinical Triage | Ward health station provides clinical triage for cases escalated by volunteers. Issues referrals to district hospital for cases requiring higher-level care. |
| --- | --- |
| Secondary Collection Point | If the sub-warehouse becomes inaccessible, the ward health station serves as a secondary EMK collection point for mobile households in the area. |
| District Hospital | District hospital receives patients escalated from ward health stations. Also coordinates with MoH on emergency medication reserve activation if EMK-3 supply is critically low. |
| EMK-3 Critically Low? | Health facilities monitor whether EMK-3 (chronic illness bridge kit) supply is critically low across their district. |
| Coordinate with MoH | If EMK-3 is critically low: health facilities coordinate directly with Ministry of Health to activate emergency medication reserve, bypassing normal supply chain timelines. |

# 🟤  LANE 5 — Local Authorities

## Phase 0 — Dry Season Preparedness

| Sign Site MOUs | Ward People's Committees sign formal agreements with Red Cross for sub-warehouse facility access — ward offices, schools, and community halls. Renewed annually. |
| --- | --- |
| Share Household Data | Ward offices share household registration data with Red Cross for vulnerability mapping. Includes household size, addresses, and registered elderly/disabled residents. |
| Agree Radio Frequencies | Civil defense and Red Cross agree on shared radio channel frequencies for coordination during flood events. Confirmed before each flood season. |
| Pre-identify Backup Sites | Local authorities help Red Cross identify a backup sub-warehouse location for each district — a second building that can be activated if the primary site floods. |

## Phase 1 — Hours 0–24

| Open Sub-WH Site | Ward People's Committee opens the agreed community building and provides Red Cross with physical access for sub-warehouse activation at Phase 1. |
| --- | --- |
| Loudspeaker Announcements | Ward uses community loudspeaker system to announce EMK collection point locations and delivery schedules to residents throughout the flood event. |
| Provide Route Status | Ward officials provide Hub Managers with road and route status updates each morning and evening — including bridge closures, flooded roads, and newly passable routes. |

## Phase 2 — Hours 24–48+

| Resolve Disputes | Ward People's Committee resolves community disputes about EMK distribution (e.g., households challenging their priority score) on request from Hub Manager. |
| --- | --- |
| Evacuation Support | Civil defense provides evacuation support when water depth exceeds 80cm in any zone — triggered by Red Cross Operations Center escalation. |
| Supplemental Boats | Civil defense provides supplemental boats to Red Cross if the community boat allocation is insufficient for delivery coverage in flooded zones. |

# 🟢  LANE 6 — Logistics Partners

## Phase 0 — Dry Season Preparedness

| Truck Contract | Truck contractors sign emergency transport agreements with Red Cross — fixed price per trip, guaranteed availability during declared flood events, activated within 2 hours of Phase 1 trigger. |
| --- | --- |
| Boat Agreements | Community boat owners sign informal MOUs with Red Cross — daily rate confirmed, availability for peak flood days (Days 3–5), minimum 2 boats per sub-warehouse district. |
| Pharmacy Agreement | Pharmacy distributors sign emergency supply agreements with Red Cross — fixed emergency price list, no negotiation during flood, delivery to central warehouse within 12 hours of activation. |
| MoH Cold Storage | Ministry of Health stores EMK-3 medications at district cold storage facility year-round at 2–8°C. EMK-3 is NEVER pre-positioned at sub-warehouses. |
| Backup Truck Contract | A second logistics contractor holds a pre-signed backup transport agreement — activated only if the primary contractor fails to deliver within the agreed window. |

## Phase 1 — Hours 0–24

| Trucks Deploy | Truck convoy departs central warehouse within 2 hours of Phase 1 activation. Three trucks dispatched simultaneously to all three sub-warehouses. Hours 3–8. |
| --- | --- |
| MoH Releases EMK-3 | Ministry of Health releases EMK-3 medication stock from cold storage and transfers in insulated cold boxes to sub-warehouses. Transfer must complete within 6 hours of activation. |
| Boat Owners Confirm | Boat owners confirm availability for peak flood delivery days (Days 3–5). Minimum 2 boats confirmed per sub-warehouse district. |

## Phase 2 — Hours 24–48+

| Boats Operational | Community boats begin last-mile delivery operations in 60–80cm flood zones. Typically Days 3–5 when flooding peaks. |
| --- | --- |
| Stock below 20%? | Pharmacy distributor monitors whether stock at any sub-warehouse drops below 20% of dispatch allocation — the trigger for emergency resupply. |
| Emergency Resupply | Pharmacy distributor activates emergency resupply at fixed contract price. Delivers to central warehouse within 12 hours. Red Cross redistributes from central warehouse to affected sub-warehouses. |
| Continue Standard Ops | Stock levels adequate — no emergency resupply needed. Pharmacy distributor continues normal standby status. |