REMA RAPID EMERGENCY MEDICAL ACCESS

OPERATING PROTOCOL

Field Reference Document — All Phases

| Organizer | Viet Nam Red Cross |
| --- | --- |
| Target City | Ho Chi Minh City (or comparable Vietnamese delta city) |
| Scenario | Recurrent urban flood — 5 to 7 days, 30 to 80 cm water depth |
| Critical Window | Hours 0 to 48 |
| Document Version | v1.0 — University Track Submission |
| Classification | FOR OFFICIAL USE — Red Cross Staff and Named Volunteers Only |

CRITICAL SAFETY RULE: All delivery operations are SUSPENDED when water depth exceeds 80 cm. Escalate immediately to civil defense. No exceptions.

CONTENTS OF THIS DOCUMENT

| § | Title |
| --- | --- |
| 1 | Phase 1 Activation Checklist — Hours 0 to 24 |
| 2 | Phase 2 Adaptive Delivery Checklist — Hours 24 to 48 |
| 3 | Radio Check-In Script (4 daily slots) |
| 4 | Delivery Runsheet Template |
| 5 | Incident Log Template |
| 6 | Volunteer Household Assessment Form |

SECTION 1 — PHASE 1 ACTIVATION CHECKLIST ¦ Hours 0 to 24

ACTIVATION TRIGGER: Phase 1 activates when ANY 2 of these 3 conditions are met simultaneously: (1) City/provincial flood warning Level 2 or above (2) Rainfall forecast exceeds 100 mm in 24 hours (3) Any target district reports street-level flooding

HOURS 0–3 — Alert and Mobilize

Decision-maker: Emergency Coordinator (Operations Center)

| Action | Responsible | Done |
| --- | --- | --- |
| Confirm trigger conditions — record which 2 of 3 are met | Emergency Coordinator | [ ] |
| Issue formal REMA activation order (phone + SMS to all Hub Managers) | Emergency Coordinator | [ ] |
| Notify Hub Managers: District 1, District 2, District 3 on standby | Emergency Coordinator | [ ] |
| Alert volunteer team leaders in each district (via Hub Manager) | Hub Managers x3 | [ ] |
| Operations Center: pull pre-packed EMKs from central warehouse storage | Warehouse Manager | [ ] |
| Confirm Ministry of Health (MoH) contact — request EMK-3 cold chain release | Emergency Coordinator | [ ] |
| Begin REMA dashboard tracking — set phase to Phase 1 | Operations Staff | [ ] |
| Check radio equipment — confirm all 4 handsets charged and on agreed frequency | Operations Staff | [ ] |
| Record activation time: _______________ Recorded by: _______________ | — | [ ] |

HOURS 3–8 — Load and Dispatch to Sub-Warehouses

Decision-maker: Warehouse Manager + Emergency Coordinator for reallocation

| Action | Responsible | Done |
| --- | --- | --- |
| Load pre-packed EMK pallets onto trucks (3 trucks minimum) | Warehouse Manager | [ ] |
| Verify dispatch quantities against printed manifest (EMK-1 / EMK-2 / EMK-3) | Warehouse Manager | [ ] |
| Dispatch convoy simultaneously to all 3 sub-warehouse sites | Warehouse Manager | [ ] |
| Use highest-elevation road routes — avoid roads below 1.5 m elevation | Truck Drivers | [ ] |
| Hub Manager District 1: receive stock, verify count, sign manifest | Hub Manager D1 | [ ] |
| Hub Manager District 2: receive stock, verify count, sign manifest | Hub Manager D2 | [ ] |
| Hub Manager District 3: receive stock, verify count, sign manifest | Hub Manager D3 | [ ] |
| 5% spot-check: open boxes, verify contents match manifest — reject damaged stock | Hub Managers | [ ] |
| Confirm EMK-3 cold box received from MoH: seal intact, temp log shows <8°C | Hub Managers | [ ] |
| Sub-warehouse setup: raise pallets, label zones EMK-1 / EMK-2 / EMK-3, post zone map | Hub Managers | [ ] |
| Set up volunteer check-in table at sub-warehouse entrance | Hub Managers | [ ] |
| Confirm radio/phone contact with Operations Center from each sub-warehouse | Hub Managers | [ ] |
| 30% reserve confirmed at central warehouse — do NOT dispatch this stock | Warehouse Manager | [ ] |

HOURS 8–16 — Volunteer Deployment and Community Assessment

Decision-maker: Hub Managers — report to Operations Center every 4 hours

| Action | Responsible | Done |
| --- | --- | --- |
| Deploy volunteer teams on foot or motorbike for assessment (NOT delivery yet) | Hub Managers | [ ] |
| Each team assigned to pre-mapped zone — confirm zone assignment in writing | Hub Managers | [ ] |
| Volunteers complete paper household assessment forms (~3 min per household) | Volunteer Teams | [ ] |
| Collect: household size, elderly/pregnant/disabled, chronic illness, medication status | Volunteer Teams | [ ] |
| Teams return to sub-warehouse every 4 hours to submit completed forms | Volunteer Teams | [ ] |
| Hub Manager compiles forms — first demand estimate sent to Ops Center (WhatsApp/SMS) | Hub Managers | [ ] |
| Report any route blockages found during assessment runs immediately | Team Leaders | [ ] |
| Log route water depths by zone for routing decisions | Hub Managers | [ ] |
| First radio check-in at 08:00 if already past that time, or set for 12:00 | Hub Managers | [ ] |

HOURS 16–24 — First Demand Picture and Reallocation Decision

Decision-maker: Emergency Coordinator — reallocation window before roads deteriorate further

| Action | Responsible | Done |
| --- | --- | --- |
| Operations Center compiles all district demand reports into consolidated estimate | Operations Staff | [ ] |
| Emergency Coordinator reviews: does any sub-warehouse need resupply before Hour 24? | Emergency Coordinator | [ ] |
| If YES — dispatch emergency resupply convoy from central warehouse reserve before roads close | Emergency Coordinator | [ ] |
| Begin first delivery runs — CRITICAL band (15-20 pts) households only at this stage | Hub Managers | [ ] |
| Confirm delivery mode per zone matches current water depth (see delivery mode table) | Hub Managers | [ ] |
| Update REMA dashboard with Phase 1 demand summary and resupply status | Operations Staff | [ ] |
| Prepare prioritized household list for Phase 2 — sorted Critical > High > Medium > Standard | Hub Managers | [ ] |
| Phase 1 complete — operations continue into Phase 2 at Hour 24 | Emergency Coordinator | [ ] |

SECTION 2 — PHASE 2 ADAPTIVE DELIVERY CHECKLIST ¦ Hours 24 to 48

DELIVERY MODE TABLE — Check Water Depth Before Each Run

| Water Depth | Delivery Mode | Carry Capacity | EMKs per Trip |
| --- | --- | --- | --- |
| 0 – 30 cm | Motorbike with waterproof pannier bags | ~25 kg | 5x EMK-1 or 3x EMK-2 |
| 30 – 60 cm | Cargo bicycle or volunteer on foot with backpack | ~10–20 kg | 2–4x EMK-1 or 1–2x EMK-2 |
| 60 – 80 cm | Small motorized boat or inflatable raft | ~150 kg | 30x EMK-1 or 20x EMK-2 |
| > 80 cm | DELIVERY SUSPENDED — Escalate to civil defense immediately | — | — |

DELIVERY PRIORITY ORDER

| Band | Score | Action |
| --- | --- | --- |
| CRITICAL | 15–20 pts | Deliver in current run — goes first |
| HIGH | 10–14 pts | Deliver same day |
| MEDIUM | 5–9 pts | Deliver within 48 hours |
| STANDARD | 0–4 pts | Community collection point self-pickup |

PHASE 2 DAILY OPERATIONS CHECKLIST — Repeat Each Day

| Action | Responsible | Done |
| --- | --- | --- |
| Confirm water depth per zone before dispatching teams — update delivery mode if needed | Hub Manager | [ ] |
| Dispatch Team A (zone 1) at 07:00 — prioritized list confirmed | Hub Manager | [ ] |
| Dispatch Team B (zone 2) at 07:00 — prioritized list confirmed | Hub Manager | [ ] |
| Dispatch Team C (zone 3) at 07:00 — prioritized list confirmed | Hub Manager | [ ] |
| 08:00 Radio check-in — report stock, incidents, morning plan to Operations Center | Hub Manager | [ ] |
| Teams return between runs to restock and report new critical cases found in field | Team Leaders | [ ] |
| 12:00 Radio check-in — delivery progress, new critical cases, route issues | Hub Manager | [ ] |
| Stock check: if any EMK type falls below 30% of original allocation — report SCARCITY to EC immediately | Hub Manager | [ ] |
| Second delivery dispatch at 11:00 — address new critical cases reported in morning | Hub Manager | [ ] |
| 16:00 Radio check-in — afternoon delivery summary, resupply needs | Hub Manager | [ ] |
| Third delivery dispatch at 15:00 if stock and daylight allow | Hub Manager | [ ] |
| If water depth in any zone exceeds 80 cm — suspend all delivery, escalate to civil defense | Hub Manager | [ ] |
| All signed delivery receipts submitted by returning teams — logged in stock ledger | Hub Manager | [ ] |
| 20:00 Radio check-in — end-of-day stock count, next-day plan, overnight incidents | Hub Manager | [ ] |
| Operations Center updates dashboard with district delivery totals | Operations Staff | [ ] |
| Emergency Coordinator reviews: any cross-district reallocation needed before next morning? | Emergency Coordinator | [ ] |

SECTION 3 — RADIO CHECK-IN SCRIPT ¦ 4 Fixed Daily Slots

Use this script when phone/internet is unavailable. All Hub Managers report to Operations Center at exactly 08:00, 12:00, 16:00, and 20:00. Use agreed radio frequency. Keep transmissions under 3 minutes.

08:00 — MORNING CHECK-IN

| HUB MANAGER CALLS: | "Operations, this is Hub [District Number]. Morning check-in. Over." |
| --- | --- |
| OPS CENTER RESPONDS: | "Hub [District], Operations. Send your report. Over." |
| 1. STOCK STATUS: | "EMK-1: [remaining] units. EMK-2: [remaining] units. EMK-3: [remaining] units." |
| 2. OVERNIGHT INCIDENTS: | "[No incidents / Incident: describe briefly]." |
| 3. MORNING PLAN: | "Dispatching [number] teams to zones [list zones]. First run at 07:00." |
| 4. ROUTE STATUS: | "Routes clear / Route blocked at [location] — using alternate route." |
| 5. RESUPPLY NEEDED? | "No resupply needed / Request resupply of [EMK type, quantity]." |
| CLOSE: | "Hub [District] reporting complete. Over and out." |

12:00 — MIDDAY CHECK-IN

| HUB MANAGER CALLS: | "Operations, this is Hub [District Number]. Midday check-in. Over." |
| --- | --- |
| 1. DELIVERY PROGRESS: | "[Number] households reached this morning. [Number] CRITICAL remaining." |
| 2. NEW CRITICAL CASES: | "[Number] new critical cases identified in field. Addresses: [brief list]." |
| 3. ROUTE ISSUES: | "[No issues / Route in zone [X] now impassable — requesting boat transfer]." |
| 4. STOCK UPDATE: | "Stock now at [%] of original allocation. [Normal / Approaching scarcity threshold]." |
| 5. AFTERNOON PLAN: | "Dispatching second run at 11:00 to [zones]. Estimated [number] households." |
| CLOSE: | "Hub [District] midday complete. Over and out." |

16:00 — AFTERNOON CHECK-IN

| HUB MANAGER CALLS: | "Operations, this is Hub [District Number]. Afternoon check-in. Over." |
| --- | --- |
| 1. DELIVERY TOTAL TODAY: | "[Number] households reached total today." |
| 2. REMAINING PRIORITY: | "[Number] HIGH remaining. [Number] MEDIUM remaining." |
| 3. RESUPPLY REQUEST: | "[No resupply / Request: EMK-[type], [quantity], needed by [time].]" |
| 4. SAFETY STATUS: | "All volunteers accounted for / [Issue: describe and action taken]." |
| 5. NEXT RUN: | "Third run dispatched at 15:00 / No third run — insufficient daylight." |
| CLOSE: | "Hub [District] afternoon complete. Over and out." |

20:00 — END-OF-DAY CHECK-IN

| HUB MANAGER CALLS: | "Operations, this is Hub [District Number]. End-of-day check-in. Over." |
| --- | --- |
| 1. FINAL STOCK COUNT: | "EMK-1: [remaining]. EMK-2: [remaining]. EMK-3: [remaining]. All secured." |
| 2. DAY TOTAL: | "[Number] households reached today. Running total: [cumulative]." |
| 3. INCIDENTS TODAY: | "[No incidents / Incident log entry [ref]: describe and status]." |
| 4. VOLUNTEER STATUS: | "All [number] volunteers returned. [Any injuries, absences]." |
| 5. NEXT-DAY PLAN: | "Tomorrow priority: [zones]. Will need [resources] if conditions allow." |
| CLOSE: | "Hub [District] end-of-day complete. Standing by on radio overnight. Over and out." |

COORDINATION FAILURE QUICK REFERENCE

| Situation | Immediate Action | Escalation if Unresolved |
| --- | --- | --- |
| Hub Manager unreachable for more than 2 hours | Call pre-designated backup contact at sub-warehouse | EC dispatches staff physically to sub-warehouse; EC assumes Hub Manager authority temporarily |
| Volunteer team more than 2 hours overdue from delivery run | Hub Manager calls Team Leader, then individual volunteers | After 30 min no contact: notify civil defense with last known route and team size |
| Local authority withdraws sub-warehouse access mid-operation | Hub Manager contacts Emergency Coordinator immediately | EC calls district-level authority (above ward); Hub Manager activates backup sub-warehouse |
| Logistics partner fails to deliver trucks in agreed window | EC contacts backup contractor (second pre-signed agreement) | EC contacts civil defense for vehicle support; stock sub-warehouses sequentially by priority district |

SECTION 4 — DELIVERY RUNSHEET TEMPLATE ¦ One per Delivery Run

| RUN DETAILS |  |  |  |
| --- | --- | --- | --- |
| Sub-Warehouse / District: | _________________________ | Run #: | Date: _______________ |
| Team Number: | Team Leader: _________________________ | Departed: | Returned: __________ |
| Zone: | Water Depth at Departure: ________ cm | Delivery Mode: | MOTORBIKE / BICYCLE / BOAT (circle one) |
| Volunteers on team: | ____________________________________________________________________________ |  |  |

HOUSEHOLD DELIVERY LOG

| # | Household Name | Address | Score | Band | EMK Type | Qty | Delivered | Signature / Thumbprint | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  | [ ] |  |  |
| 2 |  |  |  |  |  |  | [ ] |  |  |
| 3 |  |  |  |  |  |  | [ ] |  |  |
| 4 |  |  |  |  |  |  | [ ] |  |  |
| 5 |  |  |  |  |  |  | [ ] |  |  |
| 6 |  |  |  |  |  |  | [ ] |  |  |
| 7 |  |  |  |  |  |  | [ ] |  |  |
| 8 |  |  |  |  |  |  | [ ] |  |  |
| 9 |  |  |  |  |  |  | [ ] |  |  |
| 10 |  |  |  |  |  |  | [ ] |  |  |
| 11 |  |  |  |  |  |  | [ ] |  |  |
| 12 |  |  |  |  |  |  | [ ] |  |  |

RUN SUMMARY

| Total households reached: | ________ | Total EMKs delivered: | ________ |
| --- | --- | --- | --- |
| EMK-1 delivered: | ________ | EMK-2 delivered: | ________ |
| EMK-3 delivered: | ________ | New critical cases found: | ________ |
| Route deviations: | ________ | Incidents reported: | ________ |

| Team Leader Signature: | ________________________________ | Hub Manager Sign-off: | ________________________________ |
| --- | --- | --- | --- |

SECTION 5 — INCIDENT LOG TEMPLATE ¦ Sub-Warehouse Record

| District: | ___________________________ | Hub Manager: | ___________________________ |
| --- | --- | --- | --- |
| Flood Event Dates: | ___________________________ | Log Started: | ___________________________ |

| RT — Route Blocked | VS — Volunteer Safety | SS — Stock Scarcity | BF — Building Flooded | OT — Other |
| --- | --- | --- | --- | --- |

| # | Date / Time | Type | Reported By | Description | Status | Resolved By | Resolved At |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  | OPEN |  |  |
| 2 |  |  |  |  | OPEN |  |  |
| 3 |  |  |  |  | OPEN |  |  |
| 4 |  |  |  |  | OPEN |  |  |
| 5 |  |  |  |  | OPEN |  |  |
| 6 |  |  |  |  | OPEN |  |  |
| 7 |  |  |  |  | OPEN |  |  |
| 8 |  |  |  |  | OPEN |  |  |
| 9 |  |  |  |  | OPEN |  |  |
| 10 |  |  |  |  | OPEN |  |  |

CONTINGENCY DECISIONS LOG

All ad-hoc decisions (route deviations, backup sub-warehouse activation, unplanned collection points) must be logged here.

| # | Date / Time | Decision Made | Reason | Authorised By |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |

SECTION 6 — VOLUNTEER HOUSEHOLD ASSESSMENT FORM ¦ ~3 Minutes per Household

INSTRUCTIONS: Complete one form per household. Circle or tick the correct score for each category. Add up the total at the bottom. Return completed forms to Hub Manager every 4 hours. You do NOT need to make a clinical diagnosis — record what you observe and what the household tells you.

| Volunteer Name: | _______________________ | Team #: | ____ | District: | ____________ |
| --- | --- | --- | --- | --- | --- |
| Date: | _______________________ | Time: | ____ | Zone: | ____________ |
| Household Address: | ___________________________________________________ |  |  | Household ID: | ____________ |
| Household Head Name: | ___________________________________________________ |  |  | Household Size: | ___ persons |

| CATEGORY 1 — MEDICAL URGENCY | Max 8 points |
| --- | --- |

|  | Circle or Tick One: | Points |
| --- | --- | --- |
| O | Life-sustaining medication (insulin, heart meds) — run out or less than 24h remaining | 8 |
| O | Chronic illness — medication low (1 to 2 days remaining) | 5 |
| O | Chronic illness — medication currently adequate | 2 |
| O | No chronic illness reported | 0 |
|  | SCORE FOR THIS CATEGORY: | _____ |

| CATEGORY 2 — HOUSEHOLD VULNERABILITY | Max 5 pts — Cap at 5 regardless of combinations |
| --- | --- |

|  | Circle or Tick One: | Points |
| --- | --- | --- |
| O | Infant under 2 years present | +2 |
| O | Pregnant woman present | +2 |
| O | Elderly person 65 or older living alone | +2 |
| O | Person with physical or cognitive disability present | +2 |
|  | SCORE FOR THIS CATEGORY: | _____ |

| CATEGORY 3 — FLOOD EXPOSURE | Max 4 points |
| --- | --- |

|  | Circle or Tick One: | Points |
| --- | --- | --- |
| O | Water inside household OR building structurally unsafe | 4 |
| O | Water at doorstep (within 10 cm of entrance) | 3 |
| O | Water in street but not reaching household | 1 |
| O | Household is dry and elevated | 0 |
|  | SCORE FOR THIS CATEGORY: | _____ |

| CATEGORY 4 — SELF-SUFFICIENCY | Max 2 points |
| --- | --- |

|  | Circle or Tick One: | Points |
| --- | --- | --- |
| O | No clean water, no food, no sanitation access | 2 |
| O | Partial access to some basic necessities | 1 |
| O | Adequate access to basic necessities | 0 |
|  | SCORE FOR THIS CATEGORY: | _____ |

| CATEGORY 5 — ISOLATION | Max 1 point |
| --- | --- |

|  | Circle or Tick One: | Points |
| --- | --- | --- |
| O | Completely isolated — no neighbors, no family, no phone signal | 1 |
| O | Some social contact or communication available | 0 |
|  | SCORE FOR THIS CATEGORY: | _____ |

| TOTAL SCORE (Add all 5 categories) | _____ / 20 |
| --- | --- |

PRIORITY BAND LOOKUP

| Score | Priority Band | Delivery Action |
| --- | --- | --- |
| 15 – 20 | CRITICAL | Deliver in current run — goes first |
| 10 – 14 | HIGH | Deliver same day |
| 5 – 9 | MEDIUM | Deliver within 48 hours |
| 0 – 4 | STANDARD | Community collection point self-pickup |

EMK TYPE RECOMMENDATION

| Situation | Recommended EMK Type |
| --- | --- |
| CRITICAL or HIGH — Chronic illness (Cat 1 score > 0) | EMK-3 (Chronic Illness Bridge Kit) |
| CRITICAL or HIGH — Infant, pregnant, elderly, disabled (Cat 2 score > 0) | EMK-2 (Vulnerable Household Kit) |
| MEDIUM or STANDARD — No special vulnerability | EMK-1 (General Household Kit) |

TIEBREAKER RULES — Apply in order if two households have the same total score

| Step 1 | Higher Category 1 score wins — medical urgency always takes precedence |
| --- | --- |
| Step 2 | Household with infant under 6 months wins |
| Step 3 | Household whose assessment form was submitted first wins |

Volunteer notes (new critical cases, unsafe conditions, refusals, observations):

| Volunteer Signature: | _________________________________ | Form Submitted (time): | __________ |
| --- | --- | --- | --- |